## Sheet1
Phase | Sprints | Focus Area | Core Deliverables | Key Metrics / Targets
Phase I | 49–52 | Real actions, developer platform, invite-only beta | Actions API, Studio UI, SDKs, rate limits, metrics | $50–100k ARR, 30d retention ≥40%
Phase I | 53–56 | Business viability, monetization, first enterprise wins | Billing, SSO, Templates marketplace, Blue/green deploys | ≥10 design partners, $100k ARR
Phase I | 57–60 | Big-ship migration path | Cloud portability (EKS/GKE), multi-model abstraction, SOC2 start | P99 stability, error <0.5%
Phase II | 61–68 | Vertical packs & partner ecosystem | Industry packs, connector SDK, telemetry dashboards | $1–3M ARR, 50 logos
Phase II | 69–74 | Reliability & margin engine | Smart routing, caching, async orchestration, unit economics | GM ≥70%, P95 <700ms
Phase II | 75–80 | Internationalization & compliance | i18n, SOC2 Type 2, ISO 27001, Slack/Teams/CLI SDKs | $5–8M ARR, EU/APAC hosting
Phase III | 81–88 | Consumer prosumer & ambient experiences | Personal Relay, mobile voice, browser/desktop agents | DAU/MAU ≥40%, ≥3 sessions/day
Phase III | 89–94 | Autonomous assists (guarded) | Policy engine, reversible autopilot, RPA fallback | Autopilot acceptance ≥60%
Phase III | 95–100 | IPO readiness & global footprint | Financial audits, security drills, multi-listing evaluation | $10B+ valuation, IPO-ready